## Construction budget
Building construction budget — plan vs actual
One row per line item: planned budget, signed contract and what was paid. See overruns per item, what's left to pay, cost per m² and per unit, and how much contingency is left.
Project | Residential building, 12 Vine St |  | Original plan (total) | 19560000 |  | Paid so far | 13260000 |  | Contingency left | 1079200
Housing units | 24 |  | Incl. contingency | 20929200 |  | Left to pay | 6590000 |  | Paid vs forecast | 66.8%
Total built area (m²) | 3200 |  | Actual cost forecast | 19850000 |  | Cost per m² | 6203.125
Contingency reserve | 7% |  | Left vs plan | -290000 |  | Cost per unit | 827083.3333
Category | Item | Supplier / contractor | Original plan | Actual agreed price | Paid | Left to pay | Variance | Variance % | Next payment | Status | Notes
Land & taxes | Land purchase | Land owners | 9500000 | 9500000 | 9500000 | 0 | 0 | 0% |  | Fully paid |  | 9500000
Design & permits | Architect | Architects office | 420000 | 450000 | 300000 | 150000 | 30000 | 7.143% | 2026-10-28 | Over budget |  | 450000
Fees & levies | Betterment levy & permit fees | Local committee | 1300000 | 1240000 | 1240000 | 0 | -60000 | -4.615% |  | Fully paid |  | 1240000
Structure | Frame floors 1-8 | Frame contractor | 6800000 | 7150000 | 2100000 | 5050000 | 350000 | 5.147% | 2026-10-19 | Over budget |  | 7150000
Plumbing | Plumbing | Plumbing contractor | 900000 |  | 0 | 900000 |  |  | 2027-01-12 | On budget |  | 900000
Lifts | 2 lifts | Lift company | 640000 | 610000 | 120000 | 490000 | -30000 | -4.688% | 2026-12-13 | On budget |  | 610000

## By category
Summary by category
Updates by itself from the budget sheet. Categories come from the Lists sheet.
Category | Original plan | Actual forecast | Difference | Paid
Land & taxes | 9500000 | 9500000 | 0 | 9500000
Design & permits | 420000 | 450000 | 30000 | 300000
Fees & levies | 1300000 | 1240000 | -60000 | 1240000
Earthworks & foundations | 0 | 0 | 0 | 0
Structure | 6800000 | 7150000 | 350000 | 2100000
Plumbing | 900000 | 900000 | 0 | 0
Electrical | 0 | 0 | 0 | 0
Waterproofing | 0 | 0 | 0 | 0
Aluminium & windows | 0 | 0 | 0 | 0
Plaster & paint | 0 | 0 | 0 | 0
Flooring & cladding | 0 | 0 | 0 | 0
Kitchens & carpentry | 0 | 0 | 0 | 0
Lifts | 640000 | 610000 | -30000 | 120000
Air conditioning | 0 | 0 | 0 | 0
Landscaping | 0 | 0 | 0 | 0
Supervision & PM | 0 | 0 | 0 | 0
Finance & bank | 0 | 0 | 0 | 0
Insurance | 0 | 0 | 0 | 0
Marketing & sales | 0 | 0 | 0 | 0
Legal | 0 | 0 | 0 | 0
Contingency | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0
Total | 19560000 | 19850000 | 290000 | 13260000

## Lists
Dropdown lists
Change, add or remove items — the dropdowns in the workbook update by themselves.
Categories
Land & taxes
Design & permits
Fees & levies
Earthworks & foundations
Structure
Plumbing
Electrical
Waterproofing
Aluminium & windows
Plaster & paint
Flooring & cladding
Kitchens & carpentry
Lifts
Air conditioning
Landscaping
Supervision & PM
Finance & bank
Insurance
Marketing & sales
Legal
Contingency
Other